## Metrics
Team: | TheBlueTeam | Units | Link to the completed GitHub Story | Link to (youtube) video illustrating the functionality of the completed story
Date (end of sprint): | 2018-04-27 |  | https://github.com/BoiseState/TeamName/issues/123 | TBD
Number of team members | 5 |  | https://github.com/BoiseState/TeamName/issues/234 | TBD
Number of planned User Stories for Sprint 2 | 10 |  | https://github.com/BoiseState/TeamName/issues/345 | TBD
Number of User Stories Completed in Sprint 2 | 6
Total user story points for planned User Stories for Sprint 2 | 80 | story points
Total user story points for completed User Stories for Sprint 2 | 40 | story points
Total effort invested by all team members in Sprint 2 | 85 | engineerHours
Number of sprints to compute velocity for | 1
Velocity | 40 | story points / sprint
Velocity/Effort | 47.06%
Total number of passing Acceptance Tests | 60
Total number of Lines of Product Code committed to master branch | 1000
Total number of Lines of Test Code committed to master branch | 800
Number of Defects Removed by "up-front" Activities | 5
Number of Defects Removed by "back-end" Activities | 8
Number of completed stories per engineer | 1.2
Number of lines of product code per engineer | 200
Number of lines of test code per engineer | 160
Ratio of Aceptance Tests/User Stories | 10
Ratio of Test/Product Lines of Code | 0.8
Total Measured Defect Density Removed | 13 | defects/KLOC
Notes:
1. Fill in the yellow cells above. Leave the other cells untouched.
2. The spreadsheet will calculate some simple metrics about your project.
Note on A3: If your count changed, record the final number for your team
Note on A8: The total number of hours contributed by all team members to sprint 1
Note on A13: You may include compiled source code including JavaScript, SQL, XML, CSS and related files. Do not include static HTML unless you have automated tests for the displayed pages (this is uncommon). Include *all* project source code.
Note on A14: You may include all automated tests. Include manual tests only if you have written scripts for a test technician to "execute" (this is uncommon).
Note on A15: You may include defects actually removed (not merely found) by any form of code review including Pair Programming.
Note on A16: You may count defects actually removed by *any* form of acceptance testing (whether you had Acceptance Criteria or not for the test) at any time during the project.