## Sprint 5
Sprint 4
Story Number | Story description | Task Number | Task Description | Priority | Estimates | Acceptance Criteria |  |  | Assigned To | Status
1 | As the user of the app, we need the app that can show the user a tour of the ccp building, so that they can find information what they want to know. | 1 | As developers we need to clean up our code, and make our app look nice and pleasing to the eye | 1 | 2 | Given that the 'home' 'about' and 'map' tabs are present, when the users open the app, then there should be a nice home page some inforamtion about the CS Department and lastly the maps of the 2nd and 3rd floor |  |  | Gerardo Flores, and Ahram Kim | In Progress
|  | 2 | As the developers we need bootstrap our project, as of now we will create a bash script, so that it works on other machines | 2 | 4 | Given that the developers write the code for the app, when they bootstrap the code and files, then the code should work well on any machine or phone for users and sponsors | Given that the developers write the code for the app, when theres a script file, then our code should not break. | Given that the developers have code and a script, when the files are done compiling and running without breaking the app should be displayed to function | Gerardo Flores, and Ahram Kim | In Progress
|  | 3 | As the developers we need to work on documentaion, for future students and for our sponsor. And work on our Readme and refactoring code | 3 | 2 | Given that the code is done, when other students working on this project open the code files, then there should be documentaion about files | GIven that the code is done, when the other students open the code, then they should see a readme file so they can better understand the code. | Given that the code is done, when the students open up the code, then refactroring our code can allow them to understand how read the code itself | Gerardo Flores, and Ahram Kim | In Progress
|  |  |  | Total Story Points: | 8

## Sprint 4
Sprint 4
Story Number | Story description | Task Number | Task Description | Priority | Estimates | Acceptance Criteria |  |  |  | Assigned To | Status
1 | As the user of the app, we need the app that can show the user a tour of the ccp building, so that they can find information what they want to know. | 1 | As the developers when the user opens the app, there should be the 'map' tab and it should be presented. | 1 | 2 | Given that the 'map' pages is presented, when the users open the app, the 'map' page should have its own separate tabs. | Given that the app is presented when the users clock on the 'map' tab, there should be two navigators: 2nd floor and 3rd floor. |  |  | Gerardo Flores, and Ahram Kim | Done
|  | 2 | As the developers when the user clicks the app, there should be 2nd floor information of CCP in the 'map' tab and it should be presented. | 2 | 5 | Given that the '2nd floor' pages in 'map' tab is presented when the users open the app, there should be 2D map of 2nd floor.. | Given that the '2nd floor' pages in 'map' tab is presented when the users open the app, there should be location navigator on 2D map each room and office. | Given that the '2nd floor' pages in 'map' tab is presented when the users open the app, each room and office should have pictures or 360 panorama. | Given that the '2nd floor' pages in 'map' tab is presented when the users open the app, each room and office should have explanation or whose office. | Gerardo Flores, and Ahram Kim | Done
|  | 3 | As the developers when the user clicks the app, there should be 3rd floor information of CCP in the 'map' tab and it should be presented. | 3 | 5 | Given that the '3rd floor' pages in 'map' tab is presented when the users open the app, there should be 2D map of 3rd floor.. | Given that the '3nd floor' pages in 'map' tab is presented when the users open the app, there should be location navigator on 2D map each room and office. | Given that the '3rd floor' pages in 'map' tab is presented when the users open the app, each room and office should have pictures or 360 panorama. | Given that the '3rd floor' pages in 'map' tab is presented when the users open the app, each room and office should have explanation or whose office. | Gerardo Flores, and Ahram Kim | Done
|  |  |  | Total Story Points: | 12

## Sprint 3
Sprint 3
Story Number | Story description | Task Number | Task Description | Priority | Estimates | Acceptance Criteria |  |  |  | Assigned To | Status
1 | As the user of the app, we need the app that can show the user a tour of the ccp building, so that they can find information what they want to know. | 1 | As the developers when the user clicks the app, there should be an icon. | 1 | 2 | Given that the app is presented when the users open their phone, then the app should have icon represented Boise state university logo. | Given that the app is presented when the users open their phone, then the app should have a name under the icon represented by Boise state university logo. | Given that the app is presented when the users click the icon, then the app should be opened and take user to the home page. |  | Gerardo Flores, and Ahram Kim | Done
|  | 2 | As the developers when the user opens the app, there should be the splashscreen before the app opens. | 2 | 2 | Given that the app is presented when the users open the app, then the splashscreen should have Boise state university logo. | Given that the app is presented when the user open the app, then the splashscreen should inform that this app is about Boise state university computer science building tour. | Give that the app is presented when the user open the app, then the splashscreen is based on blue and orange color which is represented Boise state university. | Given that the app is represented when the user open the app, then the splashscreen should end in 5 seconds and take user to the home page | Gerardo Flores, and Ahram Kim | Done
|  | 3 | As the developers when the user opens the app, there shoule be the 'about' tab and it should be presented. | 3 | 10 | Give that the 'about' pages is presented, when the users open the app, the 'about' page should have its own separate tabs . | Given that the 'about' pages is presented, when the user clicks on the 'about' page the ecosystem tab should show up and have functionality. | Given that the 'about' pages is presented, when the users clicks on the 'about' page, the contact tab should show up and function. | Given that the 'about' pages is presented, when the users clicks on the 'about' page, the degree offered tab/description should show up and take the user to information. | Gerardo Flores, and Ahram Kim | Done
|  |  |  | Total Story Points: | 14

## Sprint 2
Sprint 2
Story Number | Story description | Task Number | Task Description | Priority | Estimates | Acceptance Criteria |  |  |  | Assigned To | Status
1 | As the user of the app, we need the app that can show the user a tour of the ccp building, so that they can find information what they want to know. | 1 | As developers we need to make visual hierarchy app design before writing the code. | 2 | 2 | Given that the developers make a visual hierarchy app design for the app, we can then save time to start implementing the app. | Given that the developers make visual hierarchy app design, then visual hierchy design will allow the developers to synchronize them easily to help their workflow. | Given that the developers make visual hierarchy app design then developer can make Icon to use a clear color palette, avoid using lots of small details, and opt in for contrasting colors and a simple, clear concept. |  | Gerardo Flores, and Ahram Kim | Done
|  | 2 | As developers when the user opens the app, there should be a couple navigator tabs for the user to find the info. | 3 | 2 | Given that the app is presented, when the users open the app, then the 'home' navigator tabs should be default page of the app. | Given that the app is presented when the users open the app, then there shoule be 4 to 5 navigators tabs with each data for the app. | Given the user wants to get information of computer science major when the user opens the app, then the user must find 'about' navigator tabs to get info which what they want. | Given the user wants to get location information when the user opens the app, then the user must find 'map' navigator tabs to get info which what they want. | Gerardo Flores, and Ahram Kim | Done
|  | 3 | As developers when the user opens the app, the 'home' tab should be presented and be opened. | 4 | 5 | Given that the 'home' pages is presented, when the users open the app, the 'home' page should have the description of cs department. | Given that the 'home' page is presented when the users open the app, the 'home' page should have some of pictures of ccp building to show our building to the users. | Given that the 'home' page is presented when the users open the app, the pictures in the 'home' page should be in photo slider so we can put lots of pictures. |  | Gerardo Flores, and Ahram Kim | Done
2 |  | 1 | As developers we need to fix the errors which occurs during working on the project (make the app). | 1 | 2 | Given that we know how to fix the error when the developer make the app, then the developer can work on easily. |  |  |  | Gerardo Flores, and Ahram Kim | Done
|  |  |  | Total Story Points: | 11

## Sprint 1
Sprint 1
Story Number | Story description | Task Number | Task Description | Priority | Estimates | Acceptance Criteria |  |  |  | Assigned To | Status
1 | As a user of the app, we need an app that can show the user a tour of the ccp building, so that they can find information and their classroom. | 1 | As developers we need to get knowledge of languages we are going to use for app: php, HTML, HTML5, css, Javascript. | 1 | 2 | Given that the developers know the HTML, and HTML5 languages we will be using when we make the app, then we can create applications. | Given that the developers know the php languages we will be using when we make the app, then we can make dynamic and interactive app. | Given that the developers know the CSS languages we will be using when we make the app, then we can describe the presentation of a document written in HTML. | Given that the developers know the Javascript languages we will be using when we make the app, then we can add dynamic behavior, and make the app more fancy. | Gerardo Flores, and Ahram Kim | Done
|  | 2 | As developers we need to be familiar with ionic frame work we are going to use for app. | 2 | 2 | Given that the developers use the ionic framework when they make the app, the developers can build hybrid mobile apps which are essentially small websites running in a browser shell in an app that have access to the native plaftorm layer. | Given that the developers use the ionic framework when they make the app, the developers can handle all of the look and fell and UI interactions their app needs in order to be compelling. | Given that the developers use the ionic framework when they make the app, the developers can get with a native SDK on iOS or Android. | Given that the developers use the ionic framework when they make the app, the developers can build mobile applications that eclipse existing HTML5 development frameworks. | Gerardo Flores, and Ahram Kim | Done
2 | As a user of the app, we need to make the app to be easy to view and pleasing the eye because so that the app is easy to use. | 1 | As developers we need to collect contents to make the app about ccp building such as pictures, maps, and etc. | 3 | 1 | Given the user visits a ccp building when the user had ccp tour through website, then they can look at the map in the website how to get to ccp building. | Given the user can't visit a ccp building when the user has ccp tour through website, then they can look at the detail pictures in the website about info on ccp building. | Given the user wants to know their faculty's information (room etc..) when the user has ccp tour through website, then they can look at the information in the website. | Given that the user want to know nice views of the building or where to take a lunch/break. When the user has the site they can look up places, then they can take a break from classes. | Gerardo Flores, and Ahram Kim | Done
|  |  |  | Total Story Points: | 5